LONESTAR MOBILE SECURITY · MARKETING KIT

90-Day Go-To-Market Plan

Positioning, target customers, channels, a week-by-week plan, budgets, and the numbers that tell you it's working.

# The goal

DEFINITION OF SUCCESS By day 90: 6 towers deployed across at least 4 paying sites, 5 Google reviews, a repeatable outbound routine that books 5 consultations a week, and real photos replacing every stock image in the kit.

At $750 per tower and $150 per monitored site, six towers on four sites is roughly $5,100 in monthly recurring revenue. Everything in this plan is in service of that number.

# Positioning

| For | General contractors, yard and fleet managers, dealership GMs, property managers, and event operators in Greater Houston |
| --- | --- |
| Who | Have valuable assets sitting outdoors overnight on sites with no power or internet |
| Lonestar Mobile Security is | A local security tower rental service that delivers, deploys, and monitors solar-powered 4K camera towers |
| That | Deter theft with light, sound, and a live voice, and record everything in 4K, for less than a tenth of a guard |
| Unlike | Guards (expensive, one position, no recording), DIY cameras (need power, Wi-Fi, and someone to maintain them), or national tower companies (slow, long contracts, no local face) |
| We | Show up in days, on a monthly lease, and answer the phone |

### Messaging hierarchy

- Tagline: Eyes on your site. 24/7.

- Promise: Delivered, deployed, and monitored across Greater Houston.

- Proof points: dual 4K on a 12 ft mast · solar + LTE, zero hookups · floodlight, siren, two-way talk · plain-English alerts · live agents for $150/mo · live the same day it arrives.

- Offer: $750/mo per tower, $150/mo per monitored site, monthly lease, free site walk.

# Target customers, ranked

| Rank | Segment | Why now | Where to find them |
| --- | --- | --- | --- |
| 1 | Commercial and multifamily GCs and superintendents | Highest theft exposure, budgets for site security, projects last 6 to 24 months | Drive active sites; permit filings; AGC Houston and ABC events; LinkedIn |
| 2 | Residential builders (production and custom) | Copper and appliance theft at rough-in; many sites per builder | GHBA, subdivision sales offices, superintendents on site |
| 3 | Equipment rental and material yards | Fenced yards with fuel and machines; owners feel theft personally | Drive industrial corridors: 290, 288, 45 North, East End |
| 4 | Auto dealerships | Converter theft and lot break-ins; GMs approve fast | Dealer rows: I-45 North, Katy Freeway, Gulf Freeway, 59 Southwest |
| 5 | Property and asset managers | Vacant buildings and land between tenants; insurance pressure | IREM Houston, BOMA Houston, commercial brokers |
| 6 | Event and film operations | Short, high-value windows | NRG Park events, festival producers, Houston Film Commission list |

# Channels

| Channel | Role | Effort | Expected result by day 90 |
| --- | --- | --- | --- |
| Jobsite drop-bys + cold email | Primary. Nothing beats a face and a sell sheet at the gate. | High | 60% of consultations |
| Google Business Profile + local SEO | Capture people already searching | Medium, front-loaded | 20% of consultations; 5+ reviews |
| Referrals from customers and subcontractors | Cheapest, highest close rate | Low, ongoing | 10% of consultations, rising |
| Google Search ads | Accelerate when outbound is working | Medium | 10% of consultations at under $600 per lease |
| LinkedIn (personal profile) | Credibility with GCs and property managers | Low | Warm replies to cold email |
| Trade associations | Long-term pipeline | Medium | 2 events attended, 20 contacts |
| Direct mail (EDDM postcard) | Optional. Target industrial and dealership routes. | Low | Test one 1,000-piece route in month 3 |

# Week-by-week plan

## Days 1 to 30: Foundation and first customers

| Week | Focus | Do this |
| --- | --- | --- |
| 1 | Set up | Website live on Cloudflare; phone number, email, and booking link configured; Google Business Profile created with photos and services; social profiles published with covers; print sell sheets, cards, and signs; confirm imagery rights with the manufacturer. |
| 2 | Target list | Build a list of 50 active jobsites, 20 yards and dealerships, 10 property managers within 30 minutes of your yard. Post the first four social posts. Send the press release. |
| 3 | Outbound | Drop by 25 sites with sell sheet and card. Send 50 cold emails using the templates. Book 5 consultations. Attend one AGC or ABC event. |
| 4 | Close | Hold consultations, send same-day proposals, follow the cadence. Goal: first 2 leases signed and delivered. Photograph the deployments. |

## Days 31 to 60: Proof and repetition

| Week | Focus | Do this |
| --- | --- | --- |
| 5 | Reviews | Day-30 check-ins with first customers; ask for a Google review and a referral. Publish real deployment photos everywhere. |
| 6 | Outbound 2 | Another 25 drop-bys and 50 emails. Replace the stock imagery in the sell sheet and social with your own photos. |
| 7 | Paid | Launch Google Search with $500 to $1,000 for the month using the Ad Copy Bank; retarget website visitors on Meta. |
| 8 | Expand | Ask every active customer about their next site. Goal: 4 towers deployed, 3 reviews. |

## Days 61 to 90: Scale what worked

| Week | Focus | Do this |
| --- | --- | --- |
| 9 | Review | Read the KPI Tracker. Double the channel with the lowest cost per lease; cut the highest. |
| 10 | Segments | Run one segment-specific push (dealership row or industrial corridor) with tailored email and a landing message. |
| 11 | Referrals | Formalize the referral offer (one month of monitoring free per referred site). Tell subcontractors and suppliers too. |
| 12 | Plan next quarter | Goal: 6 towers on 4 sites, 5 reviews, a weekly routine you can hand to a second person. Decide on fleet expansion. |

# Weekly routine (once the foundation is set)

- Monday morning: update the KPI Tracker, review follow-ups due this week, post on LinkedIn.

- Tuesday and Thursday: field days. 10 to 12 jobsite drop-bys each, consultations in between.

- Wednesday: send 25 cold emails, work the follow-up cadence, one Google Business Profile post.

- Friday: proposals out, deployments scheduled, photos posted, one hour on the target list for next week.

- Every deployment day: photos, signs up, day-1 check-in scheduled.

# Budget scenarios (monthly)

| Line item | Lean ($500) | Standard ($1,500) | Aggressive ($3,000) |
| --- | --- | --- | --- |
| Google Search ads | $300 | $900 | $1,800 |
| Meta retargeting | $0 | $150 | $300 |
| Print (sell sheets, cards, signs) | $100 | $150 | $250 |
| Trade association events / dues | $50 | $150 | $300 |
| Direct mail (EDDM test) | $0 | $100 | $300 |
| Tools (Cal.com free, Google Workspace, phone line) | $50 | $50 | $50 |

One tower with monitoring pays for the Standard budget with $600 to spare. Fund ads from the second lease, not from savings.

# KPIs and targets

| Metric | Day-90 target | How to measure |
| --- | --- | --- |
| Outreach touches per week | 75 | Drop-bys + emails + calls logged in the KPI Tracker |
| Consultations booked per week | 5 | Calendar bookings + manual bookings |
| Booking rate | 10% of touches | KPI Tracker formula |
| Close rate | 35% of consultations held | KPI Tracker formula |
| Towers deployed | 6 | Count |
| Monthly recurring revenue | $5,100 | KPI Tracker formula |
| Google reviews | 5 | Google Business Profile |
| Cost per lease (paid channels) | Under $600 | Ad spend ÷ leases from ads |

# Risks and how to handle them

| Risk | Mitigation |
| --- | --- |
| Imagery rights for manufacturer-derived photos | Confirm permission before launch; replace with your own deployment photos within 30 days regardless. |
| Decision makers slow to approve a new monthly expense | Lead with the guard comparison and a one-page proposal they can forward; offer the joint 15-minute call. |
| Fleet capacity: demand outpaces towers | Track a waitlist; use it to justify the next unit. Never promise a delivery date you can't hit. |
| Monitoring expectations | Confirm response protocols with your monitoring provider and describe them accurately in every proposal. |
| Seasonality (holidays, hurricane season) | Market these as peak theft windows: 'lock in a tower before the long weekend.' |