## Launch Checklist
Launch Checklist
Work top to bottom. Change Status to Done as you go; the summary at the top updates automatically. Yellow cells are yours to edit.
Progress:
Phase | Task | Owner | Due | Status | Notes / link
Week 1: Foundation | Merge website to main and connect Cloudflare Pages; verify lonestarmobilesecurity.com loads |  |  | Done
Week 1: Foundation | Set up business phone number and add it to js/config.js |  |  | Not started
Week 1: Foundation | Create Cal.com event 'Lease Consultation' and paste link into js/config.js |  |  | Not started
Week 1: Foundation | Enable Cloudflare Email Routing for info@lonestarmobilesecurity.com |  |  | Not started
Week 1: Foundation | Install Barlow fonts; add email signature with banner |  |  | Not started
Week 1: Foundation | Order business cards (250) and sell sheets (100) |  |  | Not started
Week 1: Foundation | Order 2 jobsite signs per tower (aluminum + Coroplast) |  |  | Not started
Week 1: Foundation | Confirm rebranded imagery use with the equipment manufacturer / reseller agreement |  |  | Not started
Week 2: Be findable | Create Google Business Profile (service-area business), add photos, services, hours, booking link |  |  | Not started
Week 2: Be findable | Create Facebook Page, Instagram, LinkedIn Company Page, X; upload covers and profile picture |  |  | Not started
Week 2: Be findable | List on Yelp, Nextdoor Business, Bing Places, Apple Business Connect, Angi, Thumbtack |  |  | Not started
Week 2: Be findable | Publish first 4 social posts (Intro, Pricing, 4K, Solar) using the caption calendar |  |  | Not started
Week 2: Be findable | Send launch press release to Houston Business Journal, Realty News Report, local construction trade press |  |  | Not started
Week 3: Outbound | Build target list: 50 active jobsites, 20 yards/dealerships, 10 property managers |  |  | Not started
Week 3: Outbound | Drop by 25 jobsites with sell sheet + card; log contacts |  |  | Not started
Week 3: Outbound | Send 50 cold emails (templates in 04 Sales Tools); schedule follow-ups |  |  | Not started
Week 3: Outbound | Join AGC Houston / ABC Greater Houston / Houston Contractors Association events calendar |  |  | Not started
Week 4: Paid & referrals | Launch Google Search campaign ($500 to $1,500/mo) using Ad Copy Bank |  |  | Not started
Week 4: Paid & referrals | Launch Meta retargeting for website visitors |  |  | Not started
Week 4: Paid & referrals | Ask every deployed customer for a Google review and a referral |  |  | Not started
Ongoing | Post 3x per week on social; 1 Google Business Profile post per week |  |  | Not started
Ongoing | Photograph every new deployment; replace stock imagery with real site photos |  |  | Not started
Ongoing | Review KPI Tracker every Monday; adjust budget and outreach volume |  |  | Not started
Legend: yellow cells are for you to fill in (Owner, Due, Status, Notes). Status drop-down drives the progress line above.

## KPI Tracker
Weekly KPI Tracker
Enter the yellow columns each Monday for the prior week. Gray columns are formulas. Row 6 is an example week; overwrite it with real numbers.
Week starting | Outreach touches | Consultations booked | Consultations held | Proposals sent | Leases signed | Towers deployed (new) | Active towers (total) | Monitored sites | Ad spend ($) | Booking rate | Close rate | Cost per lease ($) | MRR ($)
2026-09-07 | 40 | 5 | 4 | 3 | 1 | 1 | 1 | 1 | 300
Totals / averages
Benchmarks to aim for in the first 90 days: booking rate 10% of outreach touches, close rate 35% of consultations held, cost per lease under $600 in paid channels. Source: Lonestar planning assumptions, adjust to your actuals.

## Assumptions
Assumptions
Blue values are inputs used by the KPI Tracker formulas.
Tower monthly rate ($) | 750
Monitoring monthly rate per site ($) | 150
Guard comparison: hourly rate ($) | 25
Guard hours per night | 12
Nights per month | 30
Guard monthly cost ($)
Break-even towers for a $1,500/mo ad budget
Source: pricing set by Lonestar Mobile Security (Sept 2026). Guard rate is a planning assumption; replace with a real quote from a Houston guard service.